## Task Tracker
POC 2 – Multi-Vendor Procurement Hub · Task Tracker
Last updated: April 2026 ¦ Scope: SAP CAP + BTP + React Frontend + S/4HANA Integration
📦 PHASE 1 — Backend & Data Model
# | Task | Category | Status | Notes
1 | Initialize SAP CAP project (cds init) | Project Setup | ✅ Done | Base scaffold with package.json, .cdsrc.json
2 | Define db/schema.cds – core entities (Shipments, ShipmentItems, Products, Vendors, PriceLedger, AuditLogs) | Data Model | ✅ Done | Temporal entity for PriceLedger; cuid + managed mixins
3 | Add purchaseOrderId & delayReason fields to Shipments | Data Model | ✅ Done | Needed for criticalDelay flow
4 | Refactor vendor Association → vendorCode: String(10) | Data Model | ✅ Done | Disconnected Association removed; aligns with S/4HANA BusinessPartner
5 | Invoice scan media stream (LargeBinary + MediaType) | Data Model | ✅ Done | invoiceScan + invoiceScan_mediaType on Shipments
6 | Define srv/procurement-service.cds – exposed entities & projections | Service Layer | ✅ Done | OData V4 draft-enabled service
7 | RBAC: xs-security.json scopes & role-templates | Security | ✅ Done | VendorUser, VendorAdmin, ProcurementManager, Auditor
8 | Fix RBAC where clause (vendorCode = $user.VendorID) | Security | ✅ Done | Invalid vendor_BusinessPartner ref removed
9 | S/4HANA remote service bindings (API_PURCHASEORDER, API_BUSINESS_PARTNER, API_PRODUCT, API_SUPPLIERINVOICE) | Integration | ✅ Done | cds.connect.to() in .cdsrc.json
10 | Implement criticalDelay action (flag delay + audit log) | Business Logic | ✅ Done | Updates status→Exception, writes AuditLog
11 | Implement approveException action (Exception→Shipped + S4 PATCH) | Business Logic | ✅ Done | S4 PATCH gracefully caught on CSRF; local status always updates
12 | Implement rejectException action (Exception→Pending) | Business Logic | ✅ Done | Clears delayReason, audit log
13 | BTP Alert Notification integration (email on criticalDelay) | Integration | ✅ Done | Direct REST call with graceful fallback when not bound
14 | Add oauth2-configuration to xs-security.json for IAS | Security | ✅ Done | redirect-uris, credential-types for external IdP
🖥️ PHASE 2 — React Frontend
# | Task | Category | Status | Notes
15 | Scaffold React + Vite + UI5 Web Components project | Project Setup | ✅ Done | vendor-portal with @ui5/webcomponents-react
16 | App.jsx routing (Dashboard, Shipments, PriceLedger, AuditLogs) | Frontend | ✅ Done | react-router-dom v7
17 | AppShell navigation sidebar | Frontend | ✅ Done | Added Audit Logs nav item
18 | Dashboard screen (KPIs, charts) | Frontend | ✅ Done | vendorCode field updated
19 | ShipmentWorkspace screen (table + detail + create) | Frontend | ✅ Done | Full OData draft flow
20 | Flag Delay dialog UI (criticalDelay with reason TextArea) | Frontend | ✅ Done | delayMutation via TanStack Query
21 | Approve Exception dialog UI (new delivery date picker) | Frontend | ✅ Done | approveMutation via TanStack Query
22 | Reject Exception inline button | Frontend | ✅ Done | rejectMutation via TanStack Query
23 | PriceLedger screen (temporal price management) | Frontend | ✅ Done | vendorCode field updated
24 | AuditLogs screen (KPIs + filters + log entries) | Frontend | ✅ Done | Auto-refresh every 30s via refetchInterval
25 | api/client.js – all API functions | Frontend | ✅ Done | triggerCriticalDelay, approveException, rejectException added
26 | TanStack Query for ALL data fetching (useQuery + useMutation) | Frontend | ✅ Done | File upload refactored to uploadMutation
🚀 PHASE 3 — BTP Deployment
# | Task | Category | Status | Notes
27 | Create mta.yaml (CAP srv + Approuter + all BTP services) | Deployment | ✅ Done | approuter.nodejs type, Alert Notification, real S/4 URL
28 | Create xs-app.json (Approuter routing config) | Deployment | ✅ Done | Routes: /procurement/* → srv-api, /* → dist
29 | Add @sap/approuter to vendor-portal/package.json | Deployment | ✅ Done | ^16 version
30 | Git push to repository | Deployment | 🔄 In Progress | Ready to push; colleague deploys from this
31 | mbt build (generate .mtar archive) | Deployment | ⏳ Pending | Run: mbt build -t mta_archives
32 | cf login + cf deploy .mtar | Deployment | ⏳ Pending | Run: cf deploy mta_archives/*.mtar
33 | Configure S4_API destination credentials in BTP Cockpit | Configuration | ⏳ Pending | BTP Cockpit → Destinations → S4_API → set User/Password
34 | Configure IAS trust in BTP Cockpit (external IdP) | Configuration | ⏳ Pending | Security → Trust Configuration → Add IAS tenant
35 | Create Alert Notification: Action (EMAIL) | Configuration | ⏳ Pending | Type: EMAIL, target: procurement manager email
36 | Create Alert Notification: Condition (Severity=HIGH) | Configuration | ⏳ Pending | Filters criticalDelay severity HIGH events
37 | Create Alert Notification: Subscription (link action+condition) | Configuration | ⏳ Pending | Wires condition → email action
✔️ PHASE 4 — Post-Deploy Testing & Verification
# | Task | Category | Status | Notes
38 | Verify app loads via Approuter URL | Testing | ⏳ Pending | Check BTP CF app URL after deploy
39 | Test login flow via XSUAA / IAS | Testing | ⏳ Pending | Vendor user login with IAS account
40 | Test RBAC: VendorUser sees only own shipments | Testing | ⏳ Pending | Assign VendorID attribute to test user in BTP Cockpit
41 | Test criticalDelay → email received by manager | Testing | ⏳ Pending | End-to-end: flag delay → check inbox
42 | Test approveException (status→Shipped, date updated) | Testing | ⏳ Pending | Verify S/4HANA PATCH works with production OAuth
43 | Test rejectException (status→Pending, reason cleared) | Testing | ⏳ Pending
44 | Test invoice PDF upload + OCR result display | Testing | ⏳ Pending | Verify LargeBinary stream endpoint
45 | Test AuditLogs screen (entries appear, filters work) | Testing | ⏳ Pending | Trigger a few events then check log
46 | Test PriceLedger temporal queries | Testing | ⏳ Pending | validFrom/validTo date filtering
47 | Performance & load check (HANA queries) | Testing | ⏳ Pending | Optional for POC; ensure no N+1 on Shipment items

## Summary
Project Summary
Phase | Total Tasks | Completed | % Done
Phase 1 – Backend & Data Model | 14 | 14 | 100%
Phase 2 – React Frontend | 12 | 12 | 100%
Phase 3 – BTP Deployment | 11 | 3 | 27.27%
Phase 4 – Post-Deploy Testing | 10 | 0 | 0%
TOTAL | 47 | 29 | 61.7%
Legend
✅ Done | Task completed
🔄 In Progress | Currently being worked on
⏳ Pending | Not yet started
🚫 Blocked | Blocked by dependency