## Task List
POC 2 – Procurement Hub: Task Tracker
No. | Task | Module / Screen | Priority | Status | Notes
1 | Git add + commit toàn bộ changes hiện tại | DevOps | High | Cần làm ngay | Message: feat: redesign draft-submit flow, RBAC, flag delay
2 | cds deploy --to sqlite (migrate proposedDeliveryDate) | Backend | High | Cần làm ngay | Chạy sau khi schema.cds thêm proposedDeliveryDate
3 | cf set-env SUPABASE_SERVICE_ROLE_KEY sau khi deploy BTP | DevOps | High | Chưa làm | Chạy: cf set-env poc2-procurement-hub-srv SUPABASE_SERVICE_ROLE_KEY '...'
4 | PDF attachment list: xem danh sách PDF đã upload | Screen 2 – Shipment Workspace | Medium | Chưa làm | Show AssetAttachments của shipment được chọn, có nút xóa
5 | Xóa PDF: delete khỏi Supabase Storage + DB | Screen 2 – Shipment Workspace | Medium | Chưa làm | API: DELETE /AssetAttachments + Supabase Storage remove
6 | Executive Dashboard – KPI Cards | Screen 1 – Dashboard | Medium | Chưa làm | Tổng shipment theo status, dùng OData $apply=aggregate
7 | Executive Dashboard – At-Risk Shipments | Screen 1 – Dashboard | Medium | Chưa làm | Shipment có deliveryDate gần + status chưa Shipped/Delivered
8 | Executive Dashboard – Shipment Chart | Screen 1 – Dashboard | Low | Chưa làm | Biểu đồ trend giao hàng theo thời gian
9 | Price Negotiation Ledger – UI Screen | Screen 3 – Price Ledger | Medium | Chưa làm | Vendor submit giá, manager xem lịch sử giá theo timeline
10 | Price Ledger – so sánh negotiatedPrice vs basePrice | Screen 3 – Price Ledger | Low | Chưa làm | Highlight khi negotiated > base (cờ đỏ)
11 | AuditLogs view cho Auditor role | Screen 2 – Shipment Workspace | Low | Chưa làm | Tab riêng hoặc màn hình riêng, chỉ Auditor/Manager thấy
12 | SupplierInvoices – hiển thị trạng thái invoice S/4HANA | Screen 2 – Shipment Workspace | Low | Chưa làm | Sau khi upload PDF, verify với SupplierInvoice API
13 | Lazy Loading các màn hình (React.lazy + Suspense) | Frontend – Performance | Low | Chưa làm | Requirement yêu cầu lazy load theo functional module
14 | Shipment Workspace – draft handling ✓ | Screen 2 – Shipment Workspace | High | Hoàn thành | Save Draft → Upload PDF → Activate flow
15 | Flag Delay + Approve/Reject Exception ✓ | Screen 2 – Shipment Workspace | High | Hoàn thành | Vendor flag delay, manager approve/reject
16 | Role-based UI via /me() endpoint ✓ | Backend + Frontend | High | Hoàn thành | isManager ẩn/hiện nút Approve/Reject
17 | Supabase service_role key (fix 403 RLS) ✓ | Backend | High | Hoàn thành | .env local, cf set-env cho BTP
18 | vendorCode auto-set khi tạo shipment ✓ | Backend | High | Hoàn thành | before('CREATE') hook
19 | PO selection trong Create Shipment dialog ✓ | Screen 2 – Shipment Workspace | Medium | Hoàn thành | Dropdown chọn PO, auto-fill vendorCode
20 | Status tự động → Shipped sau khi upload PDF ✓ | Backend | Medium | Hoàn thành | uploadInvoicePdf handler UPDATE status

## Legend
Màu Status
Hoàn thành
Cần làm ngay
Chưa làm
Màu Priority
High
Medium
Low